## Project
2.1.) Project Information
Team name | Net 1 Bier
Team members | Randolph Bock
FJ Fourie
Anton Durandt
System Breakdown
Work Breakdown and Allocation
Design circuit for security inputs(Including Door switches and PIR's) | Randolph Bock
Design circuit for output siren( to be run on 12v) | Randolph Bock
Design and implement a user interface | Randolph Bock
Design and code the SoC to handle all inputs and outputs | Randolph Bock
Order parts | Randolph Bock
Trade-off decisions | Randolph Bock
Assemble the final unit 1 as a whole | Randolph Bock
Design and implement a Direct ethernet / IP connection between SoC and Pc | Randolph Bock
Designing and implementing the backend communications | FJ Fourie
Design database for information of users and alarm systems | FJ Fourie
Design backend operator interface | FJ Fourie
Write program for backend of system to manage alarms going off and instruct operators on what to do | FJ Fourie
Integrate backend program with database | FJ Fourie
Ensure operator interface works correctly with signals received from web | FJ Fourie
Assemble the final complete project | FJ Fourie
Project Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 0% |  |  |  | Project Initiation
Week 2 | 0%
Week 3 | 5% |  |  |  | Test - Functional Analysis
Week 4 | 10% |  |  |  | Preliminary Design Complete
Week 5 | 20% |  |  |  | Members work allocation Done
Week 6 | 25% |  |  |  | Documatation Done to 25%
Week 7 | 30% |  |  |  | 30% Completion Milestone
Week 8 | 35% |  |  |  | Design on code stcutures, order components
Week 9 | 40% |  |  |  | Documatation Done to 40%
Week 10 | 40%
Week 11 | 45% |  |  |  | 50% deadline completion was not perfect (Member Anton not partcipating in group)
Week 12 | 45%
Week 13 | 60% |  |  |  | Allow for Member Anton to complete his work and participate with the group
Week 14 | 80% |  |  |  | 80% Completion Milestone( All sub systems complete, integration remaining)
Week 15 | 90% |  |  |  | Start integration between sub systems
Week 16 | 100% |  |  |  | Resolved Issue with non participating member, continuing with only 2 members (See change control N1B001)
Week 17 | 100%

## Randolph Bock
2.4.) Member A
Member name | Randolph Bock
Expertise | Software / Electronics / Documentation
Unit Breakdown
Member Work Breakdown
Design circuit for security inputs(Including Door switches and PIR's)
Design circuit for output siren( to be run on 12v)
Design and implement a user interface
Design and code the SoC to handle all inputs and outputs
Order parts
Trade-off decisions
Assemble the final unit as a whole
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 0% |  |  |  | Project Initiation
Week 2 | 0%
Week 3 | 5% |  |  |  | Test - Functional Analysis
Week 4 | 10% |  |  |  | Preliminary Design Complete
Week 5 | 15% |  |  |  | Work allocation received (alocated Unit 1)
Week 6 | 30% |  |  |  | Documentation done to 30%
Week 7 | 30% |  |  |  | Bill of materials created and evaluated
Week 8 | 35% |  |  |  | Order required commponets
Week 9 | 40% |  |  |  | 40% Completion of Documentation
Week 10 | 50% |  |  |  | 50% Completion of Documentation
Week 11 | 60% |  |  |  | Complete design of inputs and outputs for unit 1
Week 12 | 70% |  |  |  | Complete code and implemetation thereof on the SoC
Week 13 | 80% |  |  |  | Final Asembly and construction of the Alarm Panel
Week 14 | 90% |  |  |  | Complete implementation on Alarm Panel
Week 15 | 95% |  |  |  | Complete intgration with oth sub-systems
Week 16 | 100% |  |  |  | Complete all required documentation
Week 17 | 100% |  |  |  | Demonstration
Experience Report
Unit 1 of the project was allocated to me at the start of the project. Unit 1 is the Alarm panel, to complete the Unit 1, programming as well as electronic knowledge is needed.
For unit 1, interfaces had to be designed. The interfaces design for the human/machine interface is both audio and visual. Driving circuits had to be designed for these inputs & outputs.
A power supply and power protection had to be designed and built to power the SoC in the alarm panel as well as other peripherals and sensors. The power supply had to be designed according to an interface Control document, stating the connections and power constraints. The interface control document had to be set up and sign between the two parties.
After all electronic board where constructed by soldering the components to “proto-board” the system could be coded. The system runs on a SBC, the Raspberry Pi 3B running the Raspbian OS, a Linux distro. Linux commands had to be learned to operate the system, and to run the python scrip on start-up of the system.
The code for the alarm system was done in python, a coding language where I had previous experience.
The code was written in accordance to designs, flow diagrams and State machines.
Unit 1 was successfully built and tested for all requirements stated. Along with designing and building unit 1, all aspects thereof was documented, and noted.
After a Non-participating member as identified in the group (Anton Durandt), myself and FJ conducted a change control to remove the member from the group. Meeting was held with Anton to convince him to participate in the group, but after this failed the change control was filed and approved, this can be seen in change control document N1B001.
After the acceptance of the change control document, a part of unit 2, the network communications, was also allocated to me.
The network communications were done in accordance with interface control document (I/F 2), created by FJ and Myself.
Along with the design process, I also headed meetings and help with crucial design decisions.
All required team and individual documentation was done as stated.

## FJ Fourie
Member Information
Member name | FJ Fourie
Expertise | Software / Hardware / Documentation etc - can be more than one - indicate which expertise suit you best.
Unit Breakdown
Insert each member's own high-level diagram of the sub-system / module architecture and include software as part of the system. Clearly label all functional units (hardware and software) and all interfaces.
Note: High-level only for project planning purposes - detail breakdown will be part of the Specification Document of each member.
Member Work Breakdown
Design database for information of users and alarm systems
Design backend operator interface
Write program for backend of system to manage alarms going off and instruct operators on what to do
Integrate backend program with database
Ensure operator interface works correctly with signals received from web
Assemble the final complete project
Designing and implementing the backend communications
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 100% |  |  |  | Project Initiation
Week 2 | 100%
Week 3 | 100% |  |  |  | Test - Functional Analysis
Week 4 | 100% |  |  |  | Preliminary Design Complete
Week 5 | 100% |  |  |  | Work allocation received (alocated Unit 3)
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 100%
Week 11 | 100%
Week 12 | 100%
Week 13 | 100%
Week 14
Etc

## Anton Durandt
2.6.) Member C
Member name | Anton Durandt
Expertise
Unit Breakdown
Member Work Breakdown
Design and implement a Direct ethernet / ip connection between SoC and Pc
Designing and implementing the backend communications
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 0% |  |  |  | Project Initiation
Week 2 | 0%
Week 3 | 10% |  |  |  | Test - Functional Analysis
Week 4 | 10%
Week 5 | 10% |  |  |  | Work allocation received (alocated Unit 3)
Week 6 | 10%
Week 7 | 10%
Week 8 | 10%
Week 9 | 10%
Week 10 | 10%
Week 11 | 10%
Week 12 | 10%
Week 13 | 10%
Week 14 | 10%
Week 15 | 10%
Week 16 | 10% |  |  |  | Non-Participatin member removed from team, see change proposal N1B001
Week 17 | 10%

## Minutes of Meetings
2.3.) Minutes of Meetings
Meeting 1:
Date | 2017-08-08
Time | 14:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | Progress on schedule
Issues / Risks and Mitigations | Groupwork not yet distrobuted
Decisions | Functional Flow Diagram
Functional Architecture Design
Specification of interfaces
Actions | Allocated work | Randolph Bock | Specification of interfaces
|  | FJ Fourie | Functional Flow Diagram
|  | Anton Durandt | Functional Architecture Design
Meeting 2:
Date | 2017-08-21
Time | 8:00
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 15% complete
Issues / Risks and Mitigations | Time Manegment
Decisions | Members work allocation
Actions | Allocated work | Randolph Bock | User end
Unit 1
|  | FJ Fourie | Back end
Unit 3
|  | Anton Durandt | Communications link
Unit 2
Meeting 3:
Date | 2017-08-24
Time | 15:30
Chairman | Anton Durandt
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 20% complete
Issues / Risks and Mitigations | Uncertainty about 30% deadline
Decisions | Portfolio | ELO 8
ELO 5
Actions | Allocate individual and group work between members
Meeting 4:
Date | 2017-08-28
Time | 8:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 25% complete
Issues / Risks and Mitigations | Availability of PIR running on 5/3,3V
Decisions | Responsibilities
Actions | Find out about prices and availibility of components
Meeting 5:
Date | 2017-09-04
Time | 8:00
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 30% complete
Issues / Risks and Mitigations | Power distrobution
Decisions | Finilize what components are necesarry and create Bill of materials (BOM)
Actions | Get quotes for items in the BOM
Meeting 6:
Date | 2017-09-11
Time | 8:00
Chairman | Anton Durandt
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 35% complete
Issues / Risks and Mitigations | Database Design
Decisions | Code structure
Actions | Order components
Meeting 7:
Date | 2017-09-18
Time | 8:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 40% complete
Issues / Risks and Mitigations | Subject know how
Decisions | Decides who is responsible for what for 50% deadline
Actions | Start work on 50% deadline
Meeting 8:
Date | 2017-09-23
Time | 11:30
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 40% complete
Issues / Risks and Mitigations | Uncertainty about 50% deadline
Decisions | We are behind on work for 50% deadline
Actions | Work harder to complete work by 50% deadline
Meeting 9:
Date | 2017-10-09
Time | 8:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Agenda
Progress Tracking | 45% complete
Issues / Risks and Mitigations | 50% deadline completion was not perfect
Decisions | Everyone needs to work on there paperwork to complete 50%
Need to start building and coding
Need to report inactive member
Actions | Plan for the rest of the semester
File a change request with prof Holm for inactive member
Speak to Prof Holm on the state of member Anton
Meeting 10:
Date | 2017-10-16
Time | 8:00
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Agenda
Progress Tracking | 60% complete
Issues / Risks and Mitigations | Non- Participating member
Decisions | Complete all documentation for next Monday
Need to take case of inactive member further
Actions | Speak to Holm and report state of inactive member
Arange meeting with inactive member Anton
Meeting 11:
Date | 2017-10-17
Time | 9:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 60% complete
Issues / Risks and Mitigations | Non- Participating member
Decisions | Allow member chance to catch up with the work, Finish documentation for 80% completion
Actions | Work allocated for the 80% deadline
deadline set for non-participating member Anton
Meeting 12:
Date | 2017-11-08
Time | 13:30
Chairman | Prof JEW Holm
Attendance list | Prof JEW Holm
Mr Zanrich van Rensburg
Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 100%
Issues / Risks and Mitigations | Non- Participating member
Decisions | Remove Anton Durandt from the team as per change perposal N1B001
Actions | Continue actions as per change control N1B001

## Risks and Mitigations
2.2) Risk/Mitigation Register
Risk No | Date | Description of Issue / Risk | Severity | Impact | Mitigation / Action | Responsible person | Status
| Date when risk was identified | Description of issue / risk | (1-5) | What will happen when this risk event happens? | What needs to be done to reduce this risk. | Who will work on this risk.
1 | 2017-08-28 | Availability of PIR running on 5/3,3V | 1 | Circuit will need to change to use 12V PIR's correctly | Order PIR using 5/3,3 Volt as soon as possible, | Randolph Bock
|  |  |  | not to overvolt the control unit | Or change circuit to use 12V PIR's
2 | 2017-08-21 | Time Manegment | 5 | If time is not managed correctly the project will be | Work with the schedule provided | All members
rushed, affecting quality of the project
3 | 2017-08-08 | Groupwork not yet distributed | 5 | Members will not be able to work as they don't | Assigning and documenting groupwork | Randolph Bock
|  |  |  | know what they should be working on | to each member
4 | 2017-09-11 | Database Design | 3 | Database nor working or working incorrectly, | Work with Database design software and | FJ Fourie
|  |  |  | resulting in a fail of unit 3 | familiarize with the language of databases
5 | 2017-09-04 | Power distribution | 4 | Under or over power of project, ultimately leading | Do power management calculations | Randolph Bock
to the project not working
6 | 2017-09-18 | Subject know how | 5 | If one or more members do not have the necessary | Tell other members if you do not have the | All members
|  |  |  | knowledge to complete their unit | knowledge and seek help
7 | 2017-08-24 | Uncertainty about 30% deadline | 3 | We cannot complete work satisfactory and all the | Find out by asking fellow class members | Anton Durandt
|  |  |  | necessary work if we do not know what it is | and talking to the lecturer
8 | 2017-09-18 | Uncertainty about 50% deadline | 5 | We cannot complete work satisfactory and all the | Find out by asking fellow class members | FJ Fourie
|  |  |  | necessary work if we do not know what it is | and talking to the lecturer
9 | 2017-10-05 | Non-participating Member | 5 | A non-participating member, Anton Durant, results | Reallocating the work of Anton to | Randolph Bock & FJ Fourie
|  |  |  | in a critical aspect of the project not working. | Randolph and FJ
Ultimately resulting in failure of the project.

## Trade-off decicions
Trade-off decicions
Visual Human Machine interface (I/F 1):
| LCD Screen | LED's | 7-Segment | Weight
Cost | 3 | 10 | 7 | 0.5
Reliability | 6 | 9 | 7 | 0.3
Ease of use | 6 | 7 | 6 | 0.2
| 4.5 | 9.1 | 6.8
Input Human Machine interface (I/F 1):
| Remote | Turn key | Keypad | Weight
Cost | 1 | 5 | 9 | 0.5
Reliability | 2 | 2 | 8 | 0.3
Ease of use | 7 | 9 | 6 | 0.2
| 2.5 | 4.9 | 8.1
5V Voltage regulator
| LM7805 | LM371 | usb1002 | Weight
Efficiency | 3 | 4 | 8 | 0.5
Cost | 8 | 8 | 7 | 0.2
Reliability | 7 | 8 | 9 | 0.3
| 5.2 | 6 | 8.1

## Power Budget
Power Budget
Component | Qty | Power per unit | Power total | Max power: | 6W
SoC | 1 | 5W | 5W
PIR | 4 | 0,6mW | 2,4mW
Inefficiencies | 1 | 500mW | 500mW
Total: |  |  | 5,5024W

## BOM
BOM
Qty | Name | Component | Status: | Module | Price | Website
1 | 4 x 3 Matrix 12 Key Array Membrane Keypad | Keypad | Ordered & Received | 1,1,1 | 25.44 | https://www.pishop.co.za/store/keypads/4-x-3-matrix-12-key-array-membrane-keypad-keypad
1 | 2N2222 | NPN transistor | Ordered & Received | 1,1,3
1 | Raspberry Pi 3B | SoC | Ordered & Received | 1.2 | 560 | https://www.pishop.co.za/store/raspberry-pi-boards/raspberry-pi-3---model-b
8 | PHBZX79C | Zener Diode | Ordered & Received | 1.3
4 | HC-SR501 Infrared Motion Sensor | PIR Sensor | Ordered & Received | 1,3,2 | 25.44 | https://www.pishop.co.za/store/sensors/pir-infrared-motion-sensor-hc-sr501
2 | Reed Switch | Door Contact Sensor | Ordered & Received | 1,3,3
1 | usb1002 | USB Voltage Regulator | Ordered & Received | 1.4 | 34.21 | https://www.pishop.co.za/store/power-other/dual-usb-output-6-24v-to-52v-3a-dc-dc-step-down-power-converter
1 | IRF9530 | MOSFET PMOS | Ordered & Received | 1.4
10 | Screw in wire terminals | Wire terminals | Ordered & Received | All
1 | Strip board | Prototyping Board | Ordered & Received | All
1 | Raspberri Pi 3 CPU HAT Heatsink | Heatsink | Ordered & Received | All | 30.7
1 | SanDisk 16Gb SD Card | Sd Card | Ordered & Received | All | 113.16
1 | Brass Standoff spacers | Mounting hardware | Ordered & Received | All | 16.67
`