## Project
Project Information
Team name | Net 1 Bier
Team members | Randolph Bock
FJ Fourie
Anton Durandt
System Breakdown
Work Breakdown and Allocation
Design circuit for security inputs(Including Door switches and PIR's) | Randolph Bock
Design circuit for output siren( to be run on 12v) | Randolph Bock
Design and implement a user interface | Randolph Bock
Design and code the SoC to handle all inputs and outputs | Randolph Bock
Order parts | Randolph Bock
Trade-off decisions | Randolph Bock
Assemble the final unit 1 as a whole | Randolph Bock
Design and implement a Direct ethernet / IP connection between SoC and Pc | Anton Durandt
Design and implement an ethernet / IP connection via 3g between SoC and Pc | Anton Durandt
Designing and implementing the database to the cloud | Anton Durandt
Designing and implementing the database communications | Anton Durandt
Design database for information of users and alarm systems | FJ Fourie
Design backend operator interface | FJ Fourie
Write program for backend of system to manage alarms going off and instruct operators on what to do | FJ Fourie
Integrate backend program with database | FJ Fourie
Ensure operator interface works correctly with signals received from web | FJ Fourie
Assemble the final complete project | FJ Fourie
Project Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 100%
Week 11 | 100%
Week 12 | 100%
Week 13 | 100%
Week 14
Etc
Show project's overall progress on a weekly basis. In the "Description" column, indicate why work has been delayed, if at all.

## Randolph Bock
Member Information
Member name | Randolph Bock
Expertise | Software / Hardware / Documentation etc - can be more than one - indicate which expertise suit you best.
Unit Breakdown
Member Work Breakdown
Design circuit for security inputs(Including Door switches and PIR's)
Design circuit for output siren( to be run on 12v)
Design and implement a user interface
Design and code the SoC to handle all inputs and outputs
Order parts
Trade-off decisions
Assemble the final unit as a whole
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 100%
Week 11 | 100%
Week 12 | 100%
Week 13 | 100%
Week 14
Etc

## FJ Fourie
Member Information
Member name | FJ Fourie
Expertise | Software / Hardware / Documentation etc - can be more than one - indicate which expertise suit you best.
Unit Breakdown
Insert each member's own high-level diagram of the sub-system / module architecture and include software as part of the system. Clearly label all functional units (hardware and software) and all interfaces.
Note: High-level only for project planning purposes - detail breakdown will be part of the Specification Document of each member.
Member Work Breakdown
Design database for information of users and alarm systems
Design backend operator interface
Write program for backend of system to manage alarms going off and instruct operators on what to do
Integrate backend program with database
Ensure operator interface works correctly with signals received from web
Assemble the final complete project
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 100%
Week 7 | 100%
Week 8 | 100%
Week 9 | 100%
Week 10 | 100%
Week 11 | 100%
Week 12 | 100%
Week 13 | 100%
Week 14
Etc

## Anton Durandt
Member Information
Member name | Anton Durandt
Expertise | Software / Hardware / Documentation etc - can be more than one - indicate which expertise suit you best.
Unit Breakdown
Insert each member's own high-level diagram of the sub-system / module architecture and include software as part of the system. Clearly label all functional units (hardware and software) and all interfaces.
Note: High-level only for project planning purposes - detail breakdown will be part of the Specification Document of each member.
Member Work Breakdown
Design and implement a Direct ethernet / ip connection between SoC and Pc
Design and implement an ethernet / ip connection via 3g between SoC and Pc
Designing and implementing the backend communications to the SoC
Member Schedule
Progress Tracking
Project Status
| % Complete | Green | Amber | Red | Description
Week 1 | 100%
Week 2 | 100%
Week 3 | 100%
Week 4 | 100%
Week 5 | 100%
Week 6 | 0%
Week 7 | 0%
Week 8 | 0%
Week 9 | 0%
Week 10 | 0%
Week 11 | 0%
Week 12 | 0%
Week 13 | 0%
Week 14
Etc

## Minutes of Meetings
Minutes of Meetings
Meeting 1:
Date | 2017-08-08
Time | 14:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | Progress on schedule
Issues / Risks and Mitigations | Groupwork not yet distrobuted
Decisions | Functional Flow Diagram
Functional Architecture Design
Specification of interfaces
Actions | Allocated work | Randolph Bock | Specification of interfaces
|  | FJ Fourie | Functional Flow Diagram
|  | Anton Durandt | Functional Architecture Design
Meeting 2:
Date | 2017-08-21
Time | 8:00
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 15% complete
Issues / Risks and Mitigations | Time Manegment
Decisions | Members work allocation
Actions | Allocated work | Randolph Bock | User end
Unit 1
|  | FJ Fourie | Back end
Unit 3
|  | Anton Durandt | Communications link
Unit 2
Meeting 3:
Date | 2017-08-24
Time | 15:30
Chairman | Anton Durandt
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 20% complete
Issues / Risks and Mitigations | Uncertainty about 30% deadline
Decisions | Portfolio | ELO 8
ELO 5
Actions | Allocate individual and group work between members
Meeting 4:
Date | 2017-08-28
Time | 8:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 25% complete
Issues / Risks and Mitigations | Availability of PIR running on 5/3,3V
Decisions | Responsibilitys
Actions | Find out about prices and availibility of components
Meeting 5:
Date | 2017-09-04
Time | 8:00
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 30% complete
Issues / Risks and Mitigations | Power distrobution
Decisions | Finilize what components are necesarry and create Bill of materials (BOM)
Actions | Get quotes for items in the BOM
Meeting 6:
Date | 2017-09-11
Time | 8:00
Chairman | Anton Durandt
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 35% complete
Issues / Risks and Mitigations | Database Design
Decisions | Code structure
Actions | Order components
Meeting 7:
Date | 2017-09-18
Time | 8:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 40% complete
Issues / Risks and Mitigations | Subject know how
Decisions | Decides who is responsible for what for 50% deadline
Actions | Start work on 50% deadline
Meeting 8:
Date | 2017-09-23
Time | 11:30
Chairman | FJ Fourie
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 40% complete
Issues / Risks and Mitigations | Uncertainty about 50% deadline
Decisions | We are behind on work for 50% deadline
Actions | Work harder to complete work by 50% deadline
Meeting 9:
Date | 2017-10-17
Time | 9:00
Chairman | Randolph Bock
Attendance list | Randolph Bock
FJ Fourie
Anton Durandt
Agenda
Progress Tracking | 70% complete
Issues / Risks and Mitigations | Non- Participating member
Decisions | Allow member chance to catch up with the work, Finish documentation for 80% completion
Actions | Work allocated for the 80% deadline
deadline set for non-participating member Anton

## Risks and Mitigations
Risk No | Date | Description of Issue / Risk | Severity | Impact | Mitigation / Action | Responsible person | Status
| Date when risk was identified | Description of issue / risk | (1-5) | What will happen when this risk event happens? | What needs to be done to reduce this risk. | Who will work on this risk.
1 | 2017-08-28 | Availability of PIR running on 5/3,3V | 1 | Circuit will need to change to use 12V PIR's correctly not to overvolt the control unit | Order PIR using 5/3,3 Volt as soon as possible, Or change circuit to use 12V PIR's | Randolph Bock
2 | 2017-08-21 | Time Manegment | 5 | If time is not managed correctly the project will be rushed, affecting quality of the project | Work with the schedule provided | All members
3 | 2017-08-08 | Groupwork not yet distributed | 5 | Members will not be able to work as they don't know what they should be working on | Assigning and documenting groupwork to each member | Randolph Bock
4 | 2017-09-11 | Database Design | 3 | Database nor working or working incorrectly, resulting in a fail of unit 3 | Work with Database design software and familiarize with the language of databases | FJ Fourie
5 | 2017-09-04 | Power distribution | 4 | Under or over power of project, ultimately leading to the project not working | Do power management calculations | Randolph Bock
6 | 2017-09-18 | Subject know how | 5 | If one or more members do not have the necessary knowledge to complete their unit | Tell other members if you do not have the knowledge and seek help | All members
7 | 2017-08-24 | Uncertainty about 30% deadline | 3 | We cannot complete work satisfactory and all the necessary work if we do not know what it is | Find out by asking fellow class members and talking to the lecturer | Anton Durandt
8 | 2017-09-18 | Uncertainty about 50% deadline | 5 | We cannot complete work satisfactory and all the necessary work if we do not know what it is | Find out by asking fellow class members and talking to the lecturer | FJ Fourie
9 | 2017-10-05 | Non-participating Member | 5 | A non-participating member, Anton Durant, results in a critical aspect of the project not working. Ultimately resulting in failure of the project. | Reallocating the work of Anton to Randolph and FJ | Randolph Bock & FJ Fourie

## Trade-off decicions
Trade-off decicions
Visual Human Machine interface (I/F 1):
| LCD Screen | LED's | 7-Segment | Weight
Cost | 3 | 10 | 7 | 0.5
Reliability | 6 | 9 | 7 | 0.3
Ease of use | 6 | 7 | 6 | 0.2
| 4.5 | 9.1 | 6.8
Input Human Machine interface (I/F 1):
| Remote | Turn key | Keypad | Weight
Cost | 1 | 5 | 9 | 0.5
Reliability | 2 | 2 | 8 | 0.3
Ease of use | 7 | 9 | 6 | 0.2
| 2.5 | 4.9 | 8.1
5V Voltage regulator
| LM7805 | LM371 | usb1002 | Weight
Efficiency | 3 | 4 | 8 | 0.5
Cost | 8 | 8 | 7 | 0.2
Reliability | 7 | 8 | 9 | 0.3
| 5.2 | 6 | 8.1

## Power Budget
Power Budget
Component | Qty | Power per unit | Power total | Max power: | 6W
SoC | 1 | 5W | 5W
PIR | 4 | 0,6mW | 2,4mW
Inefficiencies | 1 | 500mW | 500mW
Total: |  |  | 5,5024W

## BOM
BOM
Qty | Name | Component | Status: | Module | Price | Website
1 | 4 x 3 Matrix 12 Key Array Membrane Keypad | Keypad | Ordered & Received | 1,1,1 | 29 | https://www.pishop.co.za/store/keypads/4-x-3-matrix-12-key-array-membrane-keypad-keypad
1 | 2N2222 | NPN transistor | Ordered & Received | 1,1,3
1 | Raspberry Pi 3B | SoC | Ordered & Received | 1.2 | 560 | https://www.pishop.co.za/store/raspberry-pi-boards/raspberry-pi-3---model-b
8 | PHBZX79C | Zener Diode | Ordered & Received | 1.3
4 | HC-SR501 Infrared Motion Sensor | PIR Sensor | Ordered & Received | 1,3,2 | 29 | https://www.pishop.co.za/store/sensors/pir-infrared-motion-sensor-hc-sr501
2 | Reed Switch | Door Contact Sensor | Ordered & Received | 1,3,3
1 | usb1002 | USB Voltage Regulator | Ordered & Received | 1.4 | 39 | https://www.pishop.co.za/store/power-other/dual-usb-output-6-24v-to-52v-3a-dc-dc-step-down-power-converter
1 | IRF9530 | MOSFET PMOS | Ordered & Received | 1.4
10 | Screw in wire terminals | Wire terminals | Ordered & Received | All
1 | Strip board | Prototyping Board | Ordered & Received | All